## AWP&B 2022
|  |  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
Month
Donor | CSRWASHDEP AWB 2022 | Budget (UA) | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec
1.WASH INFRASTRUCTURE
| 1.1 Water Supply Infrastructure | 2690497.6474
ADF | Consultancy for Network design and Supervision
| Completion of Design and Tender process | 88910.6667 | bar: Month Jan to Month Apr
| Supervision of water supply infrastructure works | 65473.75 | bar: Month July to Month Dec
RWSSTF | Drilling of production boreholes (103) | 152479.9441 | bar: Month Jan to Month Apr
Water Supply works
GEF | Supply and Installation of Solar water pumping systems (Large) | 1801450.7692 | bar: Month July to Month Dec
GEF | Supply and Installation of Solar water pumping systems (Mini) | 304033.4266 | bar: Month July to Month Dec
GEF | Upgrading and Expansion of SWP systems | 278149.0909 | bar: Month July to Month Dec
| 1.2 SANITATION INFRASTRUCTURE | 683857.9057
ADF | Municipal Waste Collection Centers
Submission of Design Report | bar: Month Jan to Month Mar
RWSSIFT | Household Demonstration VIP latrine | 84900
Training of Artesian | bar: Month Jan to Month Apr
Construction of demonstation toilets | bar: Month Jan to Month Apr
RWSSIFT | Institutional Sanitation facilities - 40No | 388822.2524
Construction of Institional VIP latrines | bar: Month Jan to Month Jun
Recruitment of consultant | bar: Month Mar to Month Jun
Design work | bar: Month July to Month Sept
ADF | Waste Management Study and Landfill design | 210135.6533
Submission of Detailed Design Report | bar: Month Jan to Month Jun
RWSSTF | Consultancy for Ground water Mapping | 115875
| 2.2 Sector Coordination, monitoring & performance strengthering Including TAs | 592701.3327
| Consultancy for the WASH mapping & Web-Based M&E Systems | 211303.775 | bar: Month Jan to Month Mar
TSF | Organise International Study Tours/Learning Visits (50% female participants) | 100000
TSF | Training of 144 Wash Committees | 20000 | bar: Month Mar to Month Dec
TSF | Train 50 MDFTs on O&M strategy/manual developed for rural WASH, including effective gender mainstreaming on Climate SMART WASH | 50000 | bar: Month May to Month Dec
TSF | Train 100 VDCs on O&M strategy/manual developed for rural WASH, including effective gender mainstreaming in Climate SMART WASH with at least 33% female representation | 50000 | bar: Month May to Month Dec
TSF | Piloting of a Regional Water Users Asso. (CRRN) & NBR | 15000 | bar: Month Apr to Month Aug
TSF | Implementation of Hygiene Promotion & Educ. | 146397.5577
| 2.3 Sector Coordination, monitoring & performance strengthering Including Tas | 518156.3427
| Project implementation Technical Assistants | 182000
| consultancy for Annual Sector Performance Review | 63986.014 | bar: Month Jan to Month Apr
| Joint sector review & Sector perforance reviews | 10000 | bar: Month May; Month Dec
| Mid-Term Review | 48671.3287 | bar: Month Jan to Month Apr
TSF | 2.4 Sector stakeholders and grass root beneficiary training
TSF | Organise National Study Tours/Learning Visits | 22700 | bar: Month Feb to Month July
RWSSI | Training of relevant WASH Sector Professionals | 150000
TSF | internship for WASH sector Young professionals | 40799
| 4.1 Project Management Unit | 208182 | bar: Month Feb; Month Jun; Month Sept; Month Dec
ADF | ESMP Monitoring | 14000
ADF | Office Consumables | 7500
ADF | Project Implementation Admin Staff | 33500
ADF | Project Implementation Cost | 58000
ADF | Performance Incentive | 40250
ADF | Vehicle Operation and Maintenance | 14500
ADF | Field Travel Allowances | 30000 | bar: Month Mar; Month Jun; Month Sept; Month Dec
ADF | M & E Field Visits (Field Allowance/Per diem) | 5832 | bar: Month Mar; Month Jun; Month Sept; Month Dec
ADF | External Audit | 4600
| Total Budget for all the components | 4693395.2285
| AVAILABLE FUNDS | 2309761.9418
| FUNDS NOT AVAILABLE | 2383633.2867
Note on C11: User: 20% of contract value
Note on C20: User: Bid price

## GEF
|  |  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
Donor | Acttivities | Budget (UA) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
GEF | Supply and Installation of Solar water pumping systems (Large) | 1801450.7692 | bar: 3rd Quarter Jul to 4th Quarter Dec
GEF | Supply and Installation of Solar water pumping systems (Mini) | 304033.4266 | bar: 3rd Quarter Jul to 4th Quarter Dec
GEF | Upgrading and Expansion of SWP systems | 278149.0909 | bar: 3rd Quarter Jul to 4th Quarter Dec
| Total | 2383633.2867
Note on C4: User: 20% of contract value

## GCF
|  |  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
Donor | Acttivities | Budget (UA) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
GCF | Drilling of Observation boreholes (50) | 239774 | bar: 3rd Quarter Jul to 4th Quarter Dec
GCF | 1.4 B Reha of dumpsites, Matrl Recovey flties &Compositing flties | 95452.7273
GCF | Procurement of waste Collection vehicles | 874741.2587
GCF | Procurement of hydrological monioring equipment for DWR | 225206 | bar: 3rd Quarter Jul to 4th Quarter Dec
GCF | Design, Supply and Installation of Drip Irrigation Kits in Schools | 337145.4178 | bar: 3rd Quarter Jul to 4th Quarter Dec
GCF | 3.1 Water Resource Mgt for Improved Livelihood
Total
Note on C10: User: all activities funded by GCF